## Sheet1
Task Group | Task Name | Scope | Status | Blocker | USER COMMENTS FOR COPILOT | Copilot remarks (DATETIME) | Copilot New remarks (DATETIME) | Copilot New remarks (DATETIME)
Cross-Surface UX | Navigation, usability & state | UX-01 through UX-06 ¦ Setup/app navigation, consistent builder interactions, working controls, save/error/dirty states, accessibility and consistency across runtime and previews. | Partial |  |  | Flow Builder unsaved-state indicators and discard/navigation protections are documented and build-checked; the cross-surface UX acceptance criteria have not been fully verified. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Object Manager | Object and field foundations | OBJ-01 through OBJ-27 ¦ Object catalog/lifecycle/properties; field and relationship creation, type-specific configuration, formulas, lookup filters, editing, dependencies and safe deletion. | Not Audited |  |  | No item-by-item Object Manager evidence audit has been recorded in the current tracker pass. This means unknown, not evidence that no work was done. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Object Manager | Setup sections and runtime use | OBJ-28 through OBJ-45 ¦ Layouts, record pages, actions, compact layouts, field sets, record types, lookup filters, search/list settings, limits, metadata consumers, access, traceability and verification. | Not Audited |  |  | No item-by-item evidence audit recorded yet. The existing Object Manager UI is not being classified as absent; completion status needs a focused check. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Flow Builder | Lifecycle, versions & builder | FLOW-01, FLOW-03 ¦ Create/save/clone/version/activate/deactivate/delete; canvas, toolbox, property editing, navigation, undo/redo and unsaved-change safety. | Partial |  |  | Project notes document verified clone/version/restore/deactivation safeguards, descriptions and unsaved-change protections. Full lifecycle and interactive canvas acceptance remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Flow Builder | Types, triggers & asynchronous paths | FLOW-02, FLOW-06, FLOW-11 ¦ Flow types/invocation, Start configuration, record/schedule/event triggers, waits, durable work, resume/retry/cancellation and transaction behavior. | Partial |  |  | Platform Event-Triggered flows, event publishing/dispatch and record-triggered scheduled paths have tested implementation slices. Restart recovery, retries, permissions and full trigger matrix remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Flow Builder | Elements, resources & screens | FLOW-04 through FLOW-09 ¦ Standard elements and paths; variables/formulas; screens/interviews; record data operations; validation, availability, resource mapping and runtime outcomes. | Partial |  |  | Rollback, Choice Lookup/Section, Subflow mappings and focused runtime cases are documented/tested; formula audit is started. The complete native catalog and end-to-end behavior remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Flow Builder | Actions, security & operations | FLOW-10, FLOW-12 through FLOW-16 ¦ Actions/integrations, debug/run, logs/interviews, metadata/security, reference inventory, authoring/runtime contract and invocation traceability. | Partial |  |  | Notes document first-party actions/approval setup, typed Run/Debug, interview operations, JSON portability and permission checks. Full action/reference coverage, browser verification and async/security cases remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Lightning Page Builder | Page authoring & lifecycle | PAGE-01 through PAGE-06 ¦ App/Home/Record page creation and lifecycle, templates/layout, component palette/configuration, activation/assignments and page runtime. | Partial |  |  | Record Page clone/deactivation behavior has focused evidence; broader page kinds, composition, assignment and runtime criteria remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Lightning Page Builder | Apps, components & integration | PAGE-07 through PAGE-12 ¦ App configuration, shared component ecosystem, Object Manager integration, reference inventory, authoring round-trips and context/app integration. | Not Audited |  |  | No grouped evidence audit recorded for this workstream yet. Status is unknown, not a claim that these features are missing. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Report Builder | Authoring, lifecycle & filters | REPORT-01 through REPORT-06 ¦ Report discovery/create/edit/clone/save/run, outline/preview, formats, filters/logic/cross-filters, sorting and row limits. | Partial |  |  | Historical notes mark narrower Report Builder Phases 1 and 2 complete; that is not completion of the expanded master criteria. Clone, preview and selected filter/limit slices also have tests; full acceptance remains open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Report Builder | Results, access & demonstrated workflows | REPORT-07 through REPORT-12 ¦ Folders/charts, authorization, persistence, type/field inventory, authoring-to-result consistency and demonstrated report examples. | Partial |  |  | Opportunity matrix/tabular, Closed Cases and Leads-by-Lead-Source data paths are documented/tested; fiscal-period behavior is covered. Full UI, inventory and downstream consistency remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Dashboard Builder | Authoring, widgets & layout | DASH-01 through DASH-05 ¦ Dashboard lifecycle, widget types/configuration, responsive placement, filters and eligible source-report workflows. | Partial |  |  | Authenticated browser notes verify dashboard create/publish/view/snapshot/reload, chart/table, filter and reorder/resize paths; report-backed Lead Source workflow is tested. Full widget/workflow coverage remains open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Dashboard Builder | Sharing, identity & delivery | DASH-06 through DASH-13 ¦ Folders/sharing, running identity, data security, refresh/snapshots/subscriptions, rendering, full reference inventory, end-to-end behavior and dependencies. | Partial |  |  | Access revocation/dependency and snapshot slices are documented. A focused smoke test has a fixture-related row-count failure requiring rerun; complete identity/delivery/browser coverage remains open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
Metadata & Components | Metadata lifecycle, dependencies & portability | META-01 through META-07 ¦ Authoritative metadata, lifecycle, components, dependencies, persistence/migrations, import/export/deploy and avoiding unsupported caps. | Partial |  |  | Lead metadata migration and dependency guards have tests; identified arbitrary limits were removed in covered paths. Full cross-surface metadata consumption and portability audit remains open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
RBAC & Sharing | Effective access and tenant security | RBAC-01 through RBAC-08 ¦ Users/principals, permission composition, object/field/record access, sharing, setup authorization, identity/session controls, tenant isolation and denial/audit behavior. | Partial |  |  | Flow run/debug and dashboard/report access-denial/revocation cases are documented in tests. The complete cross-surface permission matrix and tenant-isolation acceptance remain open. Status assessed from recorded evidence. 2026-10-09 10:47 BST
QA & Release | Traceability, regression & completion evidence | QA-01 through QA-05 ¦ Evidence per requirement, automated regression, authenticated browser workflows, type/build/test gates and accurate user-facing status. | Partial |  |  | Focused tests/builds and browser paths are recorded, but requirement-wide traceability and final release gates are incomplete; one fixture-related test failure is documented. Status assessed from recorded evidence. 2026-10-09 10:47 BST