## Workstream Tracker
Task Group | Task Name | Scope / Deliverable | Status | Blocker | USER COMMENTS FOR COPILOT | Copilot remarks (DATETIME) | Copilot New remarks (DATETIME) | Copilot New remarks (DATETIME)
Report Builder | Phase 1 - Create reports (historical scope) | Earlier Report Builder checklist: report-type chooser/category/object/field search; field search and drag-drop to Outline, Filters and Preview; manual/automatic unsaved preview; create/edit/save/select/run/delete; metadata persistence and run page. | Completed |  | Historical Report Builder scope record explicitly marks Phase 1 complete and checked against the unit and regression coverage. This is the earlier, narrower scope; expanded master REPORT criteria remain tracked separately. | Historical Report Builder scope record explicitly marks Phase 1 complete and checked against the unit and regression coverage. This is the earlier, narrower scope; expanded master REPORT criteria remain tracked separately. Checked against project verification notes; 2026-10-09 10:59 BST.
Report Builder | Phase 2 - Filters (historical scope) | Earlier Report Builder checklist: standard Show Me/status/date filters; field operators and multi-value selections; Boolean logic; blank filters; filter locks/run overrides; related-child cross-filters; sorted tabular row limits. | Completed |  | Historical Report Builder scope record explicitly marks Phase 2 complete and covered by server tests. This is not a claim that all expanded master REPORT criteria are complete. | Historical Report Builder scope record explicitly marks Phase 2 complete and covered by server tests. This is not a claim that all expanded master REPORT criteria are complete. Checked against project verification notes; 2026-10-09 10:59 BST.
Report Builder | Multi-level subtotals implementation and verification | Added parent-level subtotals for Summary/Matrix reports; verified two/three-level grouping, matrix splits, date groups, nulls, numeric aggregates, hidden details, charts, and record access. | Completed |  | Historical scope record marks both subtotal implementation and its focused verification complete. | Historical scope record marks both subtotal implementation and its focused verification complete. Checked against project verification notes; 2026-10-09 10:59 BST.
Object Manager | Custom object plus custom-tab wizard path | Authenticated browser path: create custom object with launch-tab wizard, select tab style, save, and observe the object navigation entry; persisted tab style checked. | Completed |  | Positive UI and persisted-metadata path verified. Negative validation, cancel, and tab access behavior are separate remaining checks. | Positive UI and persisted-metadata path verified. Negative validation, cancel, and tab access behavior are separate remaining checks. Checked against project verification notes; 2026-10-09 10:59 BST.
Object Manager | Text field help metadata save and reload | Create a Text field with Description and Help Text; verify the field row and persisted values survive authenticated reload. | Completed |  | Save, persisted metadata and read-after-reload verified. Runtime rendering of saved help text remains in the related partial work. | Save, persisted metadata and read-after-reload verified. Runtime rendering of saved help text remains in the related partial work. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Clone saved Flow as independent Draft | Clone a saved Flow, copying elements/connectors/resources/start configuration, resetting status/version history, and creating a separate Draft. | Completed |  | Verified by flow-collection integration test and web production build; this row covers the clone behavior only. | Verified by flow-collection integration test and web production build; this row covers the clone behavior only. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Flow version snapshots and restore | Persist Flow identity/configuration in version snapshots; show version history and restore a selected snapshot as a new Draft. | Completed |  | Project notes record snapshot/history/restore implementation and focused integration assertions. Other FLOW-01 lifecycle behaviors remain separate. | Project notes record snapshot/history/restore implementation and focused integration assertions. Other FLOW-01 lifecycle behaviors remain separate. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Flow description persistence | Edit a Flow description in the manager and retain it in Flow metadata and version snapshots across edits/deactivation. | Completed |  | Integration assertions cover prior and current version descriptions. | Integration assertions cover prior and current version descriptions. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Typed saved-version Run/Debug API and authorization slices | Run saved Draft Screen/Autolaunched flows using typed inputs; validate invalid/unsupported inputs; debug outputs/trace/simulated side effects; enforce flows:run. | Completed |  | Focused Flow integration and RBAC tests cover these bounded behaviors. Browser verification and broader execution/failure contracts remain open. | Focused Flow integration and RBAC tests cover these bounded behaviors. Browser verification and broader execution/failure contracts remain open. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Roll Back Records tested runtime slice | Rollback Flow-created records and prior field updates, including nested subflow/record-trigger work; verify subsequent DML can commit. | Completed |  | Project notes record passing integration tests and full server suite (15/15) for the tested contexts. Non-record side effects and other invocation contexts are not included. | Project notes record passing integration tests and full server suite (15/15) for the tested contexts. Non-record side effects and other invocation contexts are not included. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Platform Event authoring and dispatch core | Tenant event metadata, Platform Event-Triggered Start, Publish Platform Event mappings, durable event storage and matching subscriber dispatch. | In Progress |  | Core behavior and matching/non-matching dispatch tested; restart recovery, retry/dead-letter, tenant isolation, permission denial, transaction rollback and reference coverage remain. | Core behavior and matching/non-matching dispatch tested; restart recovery, retry/dead-letter, tenant isolation, permission denial, transaction rollback and reference coverage remain. Checked against project verification notes; 2026-10-09 10:59 BST.
Flow Builder | Remaining Flow Builder parity | FLOW-01 through FLOW-16 beyond the completed slices: native types/elements, formula completeness, triggers, screens, actions, transactions, browser verification, security and reference-to-test traceability. | In Progress |  | Formula audit is explicitly started; other gaps and remaining criteria are recorded in PARITY_SCOPE_FREEZE.md. No external blocker documented. | Formula audit is explicitly started; other gaps and remaining criteria are recorded in PARITY_SCOPE_FREEZE.md. No external blocker documented. Checked against project verification notes; 2026-10-09 10:59 BST.
Lightning Page Builder | Remaining Page Builder workflows | PAGE-01 through PAGE-12: App/Home/Record page lifecycle, composition, components, activation, runtime, app context, shared components and verified authoring round-trips. | In Progress |  | Record Page clone/deactivation slices are tested. Home/App lifecycle and broader end-to-end/browser criteria remain. | Record Page clone/deactivation slices are tested. Home/App lifecycle and broader end-to-end/browser criteria remain. Checked against project verification notes; 2026-10-09 10:59 BST.
Report Builder | Phase 3 - Complete report formatting and final parity | Remaining full report formatting and master REPORT-01 through REPORT-12 verification: UI workflow, matrix/boundaries, examples, access, inventory and preview/run/dashboard consistency. | In Progress |  | Historical notes say Phase 3 was in progress and final audit incomplete; subtotal implementation/test slices above are complete, not the whole remaining scope. | Historical notes say Phase 3 was in progress and final audit incomplete; subtotal implementation/test slices above are complete, not the whole remaining scope. Checked against project verification notes; 2026-10-09 10:59 BST.
Report Builder | Demonstrated report data pathways | Opportunity tabular/matrix and Closed Cases summary examples; Leads by Lead Source fields/data; fiscal-period output. | Completed |  | Project notes document API/integration coverage for these named data paths. Broader UI workflow and full report inventory remain in the separate in-progress row. | Project notes document API/integration coverage for these named data paths. Broader UI workflow and full report inventory remain in the separate in-progress row. Checked against project verification notes; 2026-10-09 10:59 BST.
Dashboard Builder | Authenticated dashboard create-to-view path | In isolated authenticated browser: create dashboard; add chart/table; configure Lead Source filter; publish/preview; snapshot; reload/view; reorder/resize; verify persisted layout. | Completed |  | Project notes explicitly mark these paths verified and confirm saved widget order/width after reload. This is a completed path, not full DASH parity. | Project notes explicitly mark these paths verified and confirm saved widget order/width after reload. This is a completed path, not full DASH parity. Checked against project verification notes; 2026-10-09 10:59 BST.
Dashboard Builder | Remaining dashboard parity and regression | DASH-01 through DASH-13 beyond the verified browser/API slices: all widget types/properties, identity/sharing, delivery, responsiveness, authorization, dependencies and reference coverage. | In Progress |  | Project notes record multiple tested slices; full interaction/access matrix remains open. A focused RBAC smoke test has a fixture-related expected-row-count failure (7 vs 8) and needs rerun after fixture isolation. | Project notes record multiple tested slices; full interaction/access matrix remains open. A focused RBAC smoke test has a fixture-related expected-row-count failure (7 vs 8) and needs rerun after fixture isolation. Checked against project verification notes; 2026-10-09 10:59 BST.
Metadata & Components | Remaining cross-surface metadata and portability | META-01 through META-07: authoritative persistence/consumers, lifecycle, component coverage, dependency safety, migration compatibility, portability and unsupported-limit checks. | In Progress |  | Lead Street migration and report/dashboard dependency guards have documented tests; full cross-surface metadata consumer and portability audit remains. | Lead Street migration and report/dashboard dependency guards have documented tests; full cross-surface metadata consumer and portability audit remains. Checked against project verification notes; 2026-10-09 10:59 BST.
RBAC & Sharing | Remaining effective-access and isolation matrix | RBAC-01 through RBAC-08 across Flow, page, report, dashboard, metadata, sharing, record/field access, tenant isolation, setup authorization and denial/audit behavior. | In Progress |  | Specific Flow Run/Debug and dashboard/report access cases are tested. Complete cross-surface matrix and tenant-isolation verification remain. | Specific Flow Run/Debug and dashboard/report access cases are tested. Complete cross-surface matrix and tenant-isolation verification remain. Checked against project verification notes; 2026-10-09 10:59 BST.
Cross-Surface UX | Remaining navigation, accessibility and state consistency | UX-01 through UX-06: Setup/app routes, every visible control, error/dirty states, accessibility/responsive behavior, and preview/save/runtime consistency. | In Progress |  | Flow unsaved-state protections and selected browser workflows have evidence; full cross-surface interaction/accessibility verification remains. | Flow unsaved-state protections and selected browser workflows have evidence; full cross-surface interaction/accessibility verification remains. Checked against project verification notes; 2026-10-09 10:59 BST.
QA & Release | Final requirement traceability and release gates | QA-01 through QA-05: map each master criterion to evidence; regression suite, authenticated browser workflows, builds/type checks and accurate completion reporting. | In Progress |  | Focused tests/builds and browser paths are recorded but criterion-wide closeout is not complete. The dashboard fixture-related smoke failure remains to be isolated and rerun. | Focused tests/builds and browser paths are recorded but criterion-wide closeout is not complete. The dashboard fixture-related smoke failure remains to be isolated and rerun. Checked against project verification notes; 2026-10-09 10:59 BST.
Object Manager | Remaining Object Manager coverage | OBJ-01 through OBJ-45 beyond the two completed positive paths above: full object/field/relationship lifecycle, sections, runtime consumers, permissions, representative-object inventory and criterion-level verification. | In Progress |  | Source/workflow mapping and several browser/API slices are documented. Full section/conditional inventory, negative cases and complete runtime/security evidence remain open. | Source/workflow mapping and several browser/API slices are documented. Full section/conditional inventory, negative cases and complete runtime/security evidence remain open. Checked against project verification notes; 2026-10-09 10:59 BST.